## Sheet1
Serial Number | Task | Comment | Estimated time
1 | Understand the existing code base |  | 2 weeks
2 | Making the code changes for function differencing |  | 4 weeks
3 | Testing of the implemented code | This is in parallel to #2
4 | Making the code changes for visual function differencing |  | 4 weeks
5 | Testing of the implemented code | This is in parallel to #4
6 | Release